# Design Call #9

02/13/2012

14174808985609-001.mp3

Tasks

| Owner | Topic | Content | Time | Link |
| --- | --- | --- | --- | --- |
| Chris, Gary | Developmentalist Content | Need text boxes. Give access to program when new program is purchased. Prices: regular retail = $247, Early Bird = $97, Asynchronous = $197 | 0018 |  |
| Mike | Repurchase Valuesync url | Gary has emailed Mike with details | 0029 |  |
| Gary | The Flawless Individual Site | Update site | 0043 |  |
| Mike | Monthly FLOS Coaching Calls | 1x month through December with audience listening to Mike and Inner Circle folks | 0253 |  |
| Mike | Sign up Inner Circle Coaching Group | Manya already responded. Establish list of PC/PBC by the end of the 4 weeks of Mike/Jim calls | 0310 |  |
| Gary | Agenda for Call 10 | Set price for participating in monthly coaching calls | 0410 |  |
| Owner | Topic | Content | Time | Link |
| Mike | 10 Things You Get | Make a space for how we will run Mike’s Big Idea and what we’ll be adding | 0640 |  |
| Gary, Jim | Mike’s note about his direction for next 5 or 6 months | Hold for another week. Plan for discussion on Call 10. | 0710 |  |
| Gary | FLOSAPPS Intro Call | FLOSAPPS Class 5 Thursdays in March Then shift programs to 4 weeks starting on the 1st Thursday of every month from March through Dec. | 0759 |  |
| Gary | FLOSApps | Set up auto-responder stream | 2155 |  |
| Gary | 100 Day Launch Template | Create cookie cutter launch model on Sky Drive Excel spreadsheet by FEB 29 | 2350 |  |
| Gary | Mike’s style | Mike responds best to time bound single task requests | 3136 |  |
| Gary | Resurrect project template from 2011 | Last year you and Mike worked on a project template that could be used for the 100 day launch sequence | 4040 |  |
| Gary | 100 Day Rollout Model | Teach 100 Rollout Model the 4 Thursdays in June | 4830 |  |
| Jackie | 100 Day Rollout | Take Gary’s spreadsheet and enter data into Microsoft Project | 5008 |  |
| Owner | Topic | Content | Time | Link |
| Mike, Jackie | When Do People Get What | On agenda for Design Call 10 | 010600 |  |

Asks

| Owner | Topic | Content | Time | Link |
| --- | --- | --- | --- | --- |
| Gary, Mike | New Product | Market 100 Day Launch Sequence as a product – Happeneur Boilerplate | 4408 | http://jeffwalker.com/ |
| Gary | 100 Day Rollout Class | Build See page and Survey Page on different classes | 5300 |  |
| Mike | Launching an App | To launch an app you have to subscribe to Mike’s Big Idea and use format | 5424 |  |
| Mike | App Launch Policy | How the decision will be made about who launches what when to maximize “home runs” and minimize “duds” | 5540 |  |
| Mike | Market Segment | Affiliates, databases, PPC, Facebook?? | 010000 |  |
| Owner | Topic | Content | Time | Link |
| Jackie | Customer Service | Customer Service portal going live, talking about Jackie’s role as Welcome Wagon star | 010418 |  |
| Gary, Jackie | Launch Date | Need to require Happeneur site developers to set a pressure prompting launch date to create tension | 010710 |  |